## Slide 1
Good practices in preparation of EU co-financed projects
February 2026

## Slide 2
© Getty, Nes
Objectives of the presentation
EIB Advisory – short introduction
Lessons learnt
Q&A

## Slide 3: Why this presentation?
Many challenges | Ambitious new STEP context (maximizing use of different EU funds) Good projects but insufficiently presented Not all projects are relevant or mature (grant chasing)
Objectives | Help to improve the overall quality of an application, make it competitive Clarify the expectations of key areas of an application Encourage to screen out/not submit project that are not relevant/mature Help to avoid common mistakes based on previous experience
JASPERS role | Sharing of JASPERS experience and lessons learnt from other calls related to EU mandates and EU grant funding, specifically innovation and digitalisation Experience shows that a well motivated project has a higher chance of approval and has an increased chance of long-term sustainability

## Slide 4: EIB Advisory: the project support tool of the EIB
What is EIB advisory?
EIB Advisory staff offer expert guidance that helps businesses, financial intermediaries and public administrations make better investment decisions and get access to better financing.
How does it work?
We help investment happen in three ways: project support, market development and capacity building.
Why does it matter?
Tailored solutions to client’s needs. This increases the impact of our involvement and the likelihood of a project’s success. Several initiatives under one umbrella (JASPERS, Target, ELENA, PASSA, Innovation Fund etc.)

## Slide 5: Support to the eight core strategic priorities
Climate action
Digitalisation and technological innovation
Security and defence
A modern cohesion policy
Agriculture and bioeconomy
Social infrastructure
High-impact global investment
Capital markets union

## Slide 6: JASPERS – key arm of EIB Advisory
JASPERS - Joint Assistance to Support Projects in European Regions
Integral part of the EIB Advisory portfolio since 2025
JASPERS – a partnership between EC and EIB, active since 2006
Mandate co-financed from ESIF, JTF (REGIO), CEF (MOVE) + IPAIII/Ukraine (ENEST) + EIB contribution
Advisory cover the full project preparation cycle - upstream support and strategy development, project preparation and support to implementation
Includes capacity building and knowledge sharing - JASPERS Knowledge and Networking platform
100+ staff in 6 different locations (HQ in Luxembourg)

## Slide 7: Our approach
Focus will be on key sections in an Application – where the detail of the information is usually insufficient
Baseline will be a standard project Feasibility Study, aligned with the Business plan for the Call
JASPERS view and lessons-learnt based on EIB advisory involvement in:
  Preparation and screening of STEP-calls and health projects in Romania (Innovation)
  STEP activities in Poland
  Just Transition Fund Calls in the Czech Republic, including RDI and innovation in Usti
Calls financed through ERDF in different member states
Note 1: State Aid and Environmental issues will not be treated in any detail here
Note 2: It might seem obvious what information should be provided. But guidelines are often general, resulting lack in detail, inconsistencies and varying levels of quality between applications (even good projects)

## Slide 8: Summary of the Project
Purpose | To give an Executive summary of the main points from consecutive sections in the Business proposal. This will set the scene and give the Evaluator a general. Understanding of the rationale and scope of the project proposal.
Information | Keep it concise and to the point, with limited details (these will be in the body text) What is the project about (technical scope in brief)? Expected outcome/result? Put yourself in the shoes of the Evaluator. If you cannot explain easily what you want to an outsider, they cannot be expected to understand. Rationale of the project. What is the innovative nature that makes it unique or complementary OR what strategic dependencies it addresses and what is the expected result. In Czechia and in the EU. State the location(s) of the project, the Applicant and any other stakeholders Total project cost. Mention if VAT is included Be sure to mention requested grant amount
Common observations | Incomplete Executive summary Typically missing what the project de facto concerns Often only general description of project ideas, with focus more on regulatory demand than research or commercial drivers No or limited description of project stakeholders Lack in description of principal project components and project cost (VAT often missed)

## Slide 9: Demand Analysis
Purpose | A sound analysis of the market and the demand drivers is a crucial element for any project application, regardless of size. The demand analysis leads to the scope of the project and the justification of its cost. Business Proposal Demand might be spread out in several sections, so be aware to avoid unnecessary repetitions.
Information | Current demand (policy drivers and market situation) A short explanation should be given on national and EU-level policies that are the rationale for project. Reference EU strategic technologies priorities. If a market potential is a driver, it is important to explain what the current market is. Market gap filled, in EU, but as relevant also outside of EU? Size and type of competition? Market shares? If this information is not given it is difficult to justify the innovative nature, or the market potential. For STEP projects, competition should also be assessed against global strategic rivals to demonstrate European technological resilience Future demand (research and/or commercial expectations) On the basis of current market situation, demonstrate potential future volumes. Demonstrate market potential for innovative projects/ contributions to EU technological sovereignty and reduction of external dependencies. Provide quantified data, and justification behind estimations. Ideally through benchmarks.
Common observations | Information on the existing market often general and lacks competitive analysis (also from other EU countries). Projects often anchor their future demand for deliverables only on the alignment with EU, national, and regional strategies. Estimations of future uptake and use are frequently described qualitatively only, with few concrete figures on market size, growth rates, or customer segmentation. Solid benchmark data and references often missing. Lack of a gap analysis leaves uncertainty on actual commercialisation volumes (especially where private partners are involved). Letters of intent and MoU are often mentioned but facts on actual signed agreements and commitments are lacking. This adds a speculative element.

## Slide 10: Technical Scope
Purpose | To explain the technology or field of technology or research that the project wants to develop or manufacture, as well as the size, scope and location.
Information | Clear and detailed description of the technology of the project. Avoid jargon and use layman's terms, if possible A basic Multi-Criteria-Analysis is recommended. Or – at minimum - the decision process explained how the chosen technology/project was decided upon. Eligibility link. For instance, if a project is as “Innovative” it should be explained why it is so (incremental vs. breakthrough technology). Approach for developing the project. Key technical steps during implementation. Description of key components of the project (hardware, software, infrastructure/construction) to be purchased and deployed Current TRL, target TRL and TRL for different components. Indicators of success (prototypes, pilot, commercialisation, IPR etc.). Contributions to EU tech sovereignty, such as secured IPR or EU‑based industrial uptake.
Common observations | While most projects appear technically feasible, technical descriptions often remain high-level, with insufficient detail on specific methodologies, equipment specifications, or implementation steps. Gives a speculative element. Often a lack of description of methodology of how technical activities will be structured (research areas, testing, prototyping etc.). Some projects have very broad or ambitious scopes (many sub-projects, multiple technologies, lack of coherence), which may challenge effective management and timely delivery. Incoherence between planned activities and required resources (staffing, equipment, facilities). Ownership structure of equipment, in particular after completion often unclear. Can be an issue due to EU-funding rules. Lack of description of commercialisation potential and scaling beyond pilot phase. Development for the future, next phases?

## Slide 11: Institutional set-up
Purpose | To give a clear idea how the project will be organized; who the different stakeholder (applicant and partners) are in the project. What their roles are, their previous experience in the sector of the project and the rationale for their involvement.
Information | Names of all counterparts, locations, main contact points, basic company/institutional information. Demonstration of the roles of stakeholders during different phases of the project (financial, administrative, research etc.). The governance structure during the implementation phase of the project (steering committees, monitoring etc.). A clear outline of the resources from each stakeholder involved in the project, to what extent and during which phase of the project. Handling of project results (IPR, prototypes etc.). Description of approach for the commercialisation phase (if applicable) of the project results.
Common observations | Lack of realistic picture of resource availability and coordination mechanisms (i.e. missing description of project stakeholders, their unclear roles in the project, information lacking to demonstrate availability of sufficient human resources/expertise and from which project partners and in which point in time) Universities often presented as partners in a project, which helps reinforcing the innovation and research aspect. However, their contribution often appears rather as consultancy services (external expertise), lacking evidence of any role in the commercialisation phase of the project. Puts in question the partner role. Mapping of organisational structures are often missing (composition of management and project teams) Handling of IPR, ownership and strategies for operation and commercialisation often insufficient

## Slide 12: Implementation schedule
Purpose | The implementation schedule should outline the specific steps, timelines, and responsibilities required for the project delivery. Provides clarity and accountability on project progress and enables to take actions in case of delays.
Information | A GANTT chart is preferable for the overall timeline (most common) . The schedule should show the different subtasks during different project phases (Preparation and Implementation). Typically, this would cover project management, research activities, procurement, installation, testing and delivery. Each subtask should be allocated start/end date, milestones, responsible parties and dependencies on other tasks. Specifically for some activities, like research packages, separate tables can be provided, describing the different activities and the timing of the research teams.
Common observations | Implementation schedules are often kept at a very high level, lacking any detail. It suggests that there is no real awareness of complexities of the projects or the delays that can occur. There is a tendency of time-optimism. Evidence of time contingencies that can counter for delays are often ignored. The timelines are not updated before final submission of applications: that they are already outdated before the start of project. Frequent reasons for delays are often ignored in the time planning. This notably concerns: procurement, construction and recruitment (availability of resources). A general comment: projects are rarely delivered in time. It is not expected to provide a full time schedule at the time of application. However, it should be sufficently detailed to demonstrate how the project activities will be delivered and that assumptions are reasonable.

## Slide 13: Budget and financial analysis
Purpose | Its purpose is to confirm that the project represents good value for EU money. Verify that the project is realistically costed, aligned with its objectives and planned activities, and financially sustainable. This section should demonstrate that all resources and expenditures are clearly identified, justified and necessary, in line with market norms, with a transparent distinction between eligible and ineligible costs.
Information | Present relevant : CAPEX, OPEX, revenues, sources of financing. Main assumptions behind the cost calculations (benchmarking, market offers, assumptions, references to work packages). Provide accompanying calculations (e.g. in Excel form). Information of which costs are eligible / not eligible, provide information if prices are with or without VAT. Describe main assumptions behind revenues projections => this should be aligned with demand/market analysis. State the requested grant amount and the overall financing structure (own financing, grants, loans (offers)). Provide evidence for project’s financial sustainability beyond implementation phase (reference to company’s financial capacity, letters of intent for future collaboration, demonstrate experience with grant financing, etc.)
Common observations | A structured split of investment vs. non‑investment costs is usually present, with separate tables for equipment, personnel, and service. Cost tables often aligned with major project phases or work packages. Common weakness is lack of benchmark and justification of cost elements, often for human resources, which tend to be on higher end. Underestimated costs with no contingencies foreseen. Lack of information whether VAT is included in cost estimates, making true total cost uncertain. Applications often lack quantified post‑grant revenue models or cash‑flow assumptions, undermining long‑term viability once EU financing ends.

## Slide 14: Project risks analysis
Purpose | Risk analysis serves to demonstrate that the applicant has considered all relevant risk of the project and has designed credible and proportionate measures to minimise their impact. This includes verifying how risks may affect implementation, timelines, cost estimates, and the achievement of project results.
Information | Risk matrix should be provided. Comprehensive Identification of risks areas should be identified (as relevant: technical, implementation, market and commercialization, financial, operational, institutional, external (regulatory, supply chain, etc)). Qualitative risk assessement (likelihood and impact), simple scenario analysis is sufficient. Risk mitigation measures (show how mitigation reduces probability or impact). Monitoring and Risk Management system.
Common observations | Many innovative, smaller projects and research undertakings are inherently risky. Risk analysis are often high-level and far from exhaustive. This puts in question if applicant is aware of all complexities of the project. Key risk areas are often not properly identified, lower demand, delays in implementation, cost overruns, lack of specialized researchers. When identified, probability of key risks to occur tend to be underestimated and scored too low (optimistic). For projects that involves construction or the installation of equipment on premises, there is often lack of risk mitigation, especially in case of delays caused by procurement and permitting. Mitigating measures are often not clearly defined or not exhaustive.

## Slide 15: Key take-aways
High quality projects present a solid and mature design, and clearly communicate their rationale, scope, organisational structure and impact.
Market analysis is the KEY to determine the project scope (technical aspects) and its future impact and viability. The benchmark is the current market situation.
Provide evidence for your assumptions, argumentations and data. Avoid speculation
Well‑motivated, clearly structured projects score higher in evaluation but also have greater long‑term sustainability
Put yourselves in the shoes of the evaluator. Does the project fulfil eligibility criteria? Would you finance this project?

## Slide 16: Contact details: Joanna Knast-Braczkowska, Small Business and Innovation Advisory (j.knast@eib.org) Michael Schaller, Small Business and Innovation Advisory (m.schaller@eib.org)
THANK YOU!